## Project Profile
Query Tracking Sheet Template
PVV/ETR01/TMP
Project Code | GROUP - 4
Project Name | Online Banking System
Prepared/Modified by | Role | Date of Preparation
Hira Khan | Documentation | 2017-03-03
Reviewed by | Role | Date of Review
Prachi Awasthi | Documentation | 2017-03-03
Approved by | Role | Date of Approval
Tanmaya K. Acharya | Assistant Training Manager
Circulation List |  | Version Number of the template: 1.0
Version Number | <version No >

## Readme
Guidelines for usage of the Query Tracking Sheet
1 | Enter all requirements related queries raised throught project duration in this sheet to keep all queries at one place.
2 | Insert queries raised and answered in proposal phase as well into this sheet, when the project begins. This will ensure all replies and assumptions made in proposal phase are knows to the development team.
3 | Projects send/receive updated query tracking sheet to/from Capgemini. Only the latest version of the sheet should be maintained at designated place (to avoid confusion/rework). The designated locatin should be pointed to by Projects' .
4 | Projects should request Customer /Customer Collaborator(CC) to enter their queries and replies also in this sheet. Even if customer does not enter, Projects should keep this sheet updated for important queries, if queries are received by mails or documents.
5 | The status of all pending queries should be taken in the project meetings and Status Reveiw. PL should escalate to Customer Collaborator/Customer for open queries.

## Query Sheet
Query Tracking Sheet
Sr # | Type | Module | Query Text | Reply Text | Raised By (Name) | Open (Date) | Reply By (Name) | Closed (Date) | Phase Raised In | Phase Closed in | CR (Y/N) | Status | Query TAT (Turn Around Time) in days
1 | QP |  | How many actors should be included? | 2 actors needed to be included-Demand manager,Super Admin | Team 3 | 2019-08-06 | Nitin Joshi | 2019-08-06 | Requiremnt Analysis | Requiremnt Analysis |  | Closed | 1 Day
2 | QP |  | Sent ppt of the project demo for review | Reviewed by making necessary changes | Team 3 | 2019-08-06 | Nitin Joshi | 2019-08-06 | Requiremnt Analysis | Requiremnt Analysis |  | Closed | 1 Day
3 | QP |  | Which actor among demand manager and resource manager should be considered? | Demand manager | Team 3 | 2019-08-07 | Nitin Joshi | 2019-08-07 | Requiremnt Analysis | Requiremnt Analysis |  | Closed | 1 Day
4 | QP |  | Asked for database schema | Provided | Team 3 | 2019-08-07 | Nitin Joshi | 2019-08-07 | Requiremnt Analysis | Requiremnt Analysis |  | Closed | 1 day
5 | QP |  | Can we create our own database? | Yes | Team 3 | 2019-08-07 | Nitin Joshi | 2019-08-07 | Requiremnt Analysis | Requiremnt Analysis |  | Closed | 1 day
6 | QP |  | Which technology stack should be used? | Use angular 8,use highcharts,use spring with jdbc,use postgresql | Team 3 | 2019-08-07 | Nitin Joshi | 2019-08-07 | Requiremnt Analysis | Requiremnt Analysis |  | Closed | 1 day
7 | QP |  | What is the use in using same resource for demanding requests and fulfilling the requeats? | Explained the complete internal process and infrastructure of the existing project | Team 3 | 2019-08-07 | Nitin Joshi | 2019-08-07 | Requiremnt Analysis | Requiremnt Analysis |  | Closed | 1 day
8 | QP |  | Dynamic data is not getting updated in pie chart | Suggested to keep all the pie chart options in subscribe | Team 3 | 2019-08-12 | Kalpataruvu | 2019-08-12 | Coding | Coding |  | Closed | 1 day
Note on B4: QC = Q by Client QP = Q by Capgemini
Note on L4: Has this query resulted in a CR (record shd be present in the CR tracking Sheet)
Note on M4: Open Active Closed On-hold

## Revision History
REVISION HISTORY OF WORK PRODUCT (to be maintained by projects)
# | Date | Version # | Section Changed | Details of changes made | Approved By